## CommercialProposalFillingForm
| PHASE | Deliverable number | Comprehensive Social Security System PROJECT DELIVERABLES | Mandatory deliverables (Kyat) | Optional deliverables (Kyat) | Maintenance support and operation cost must be included during the 3 year project period (Kyat) | Annual maintenance support (following the end of the project period) (Kyat) | Annual operational service (Operate solution component for SSB following the end of the project period) (Kyat)
1 |  |  | PHASE 1
2 | 1 | 1.0 | Project organization manual
3 | 1 | 1.1 | Project organization manual
4
5 | 1 | 2.0 | Project management reports (payment will be monthly) | Project Management price is included across all deliverables | Project Management price is included across all deliverables
6 | 1 | 2.1 | Weekly project management report | no charge
7 | 1 | 2.2 | Monthly project monitoring report | no charge
8
9 | 1 | 3.0 | Phase 1 System design (system architecture) |  |  | Included | Not applicable | Not applicable
10 | 1 | 3.1 | Data model (entity relation diagram) ERD
11 | 1 | 3.2 | Business process model (high level documentation with the list of all events for each process)
12 | 1 | 3.3 | High level technical and software Infrastructure documentation
13 | 1 | 3.4 | Development methodology and modeling tools
14 | 1 | 3.5 | Training for main users and IT team (up to 60 people)
15 | 1 | 3.6 | Email microsoft exchange solution design (rules, strorage strategy, deployment plan)
16 | 1 | 3.7 | Pilot test strategy
17
18 | 1 | 4.0 | Data center - Main site (in collocation) |  |  | Included
19 | 1 | 4.1 | High level Datacenter solution design
20 |  | 4.2 | Processing/Computing and Storage Server, Load Balancing Device (must meet minimum requirement of section 6.2.1 Main Data Center High Level Design and refer to the detail Server specification at Appendix (I))
21 | 1 | 4.3 | Physical infrastructure, telecommunication cables, electricity connection
22 | 1 | 4.4 | Processing servers solution installation service
23 | 1 | 4.5 | Storage servers solution installation service
24 |  | 4.6 | Load balancing solution installation
25 | 1 | 4.7 | Telecommunications solution installation
26 | 1 | 4.8 | Environment set up for Development- Integration test- Training-Preproduction and Production
27 |  | 4.9 | Take Backup Solution
28 | 1 | 4.10 | Data backup mechanism deployment
29 | 1 | 4.11 | Monitoring tools deployment (servers, network,electricity, HVAC)
30 | 1 | 4.12 | Detailed inventory of all components
31 | 1 | 4.13 | Operation procedure and installation procedure for all components
32 | 1 | 4.14 | Data center integration test and trial
33 | 1 | 4.15 | SSB IT Staff training
34
35 | 1 | 5.0 | Data center secondary site (in SSB internal localtion) |  |  | Included
36 | 1 | 5.1 | High level Datacenter solution design
37 | 1 | 5.2 | Data center room construction and set up as described in Appendix(E)
38 | 1 | 5.3 | Continuous power supply system and Heat ventilation air conditionning (HVAC) installationt
39 | 1 | 5.4 | Processing/Computing and Storage Server, Load Balancing Device (must meet minimum requirement of section 6.2.1 Main Data Center High Level Design and refer to the detail Server specification at Appendix (I))
40 | 1 | 5.5 | Physical infrastructure, telecommunication cables, electricity connection
41 | 1 | 5.6 | Processing servers solution installation service
42 | 1 | 5.7 | Storage servers solution installation service
43 | 1 | 5.8 | Load balancing solution installation
44 | 1 | 5.9 | Telecommunications solution installation
45 | 1 | 5.10 | Virtual server management solution
46 | 1 | 5.11 | Environment set up for Development- Integration test- Training-Preproduction and Production
47 | 1 | 5.12 | Data backup mechanism deployment
48 | 1 | 5.13 | Monitoring tools deployment (servers, network,electricity, HVAC)
49 | 1 | 5.14 | Detailed inventory of all components
50 | 1 | 5.15 | Operation procedure and installation procedure for all components
51 | 1 | 5.16 | Data center integration test and trial
52 | 1 | 5.17 | SSB IT Staff training
53
54 | 1 | 6.0 | Telecommunication infrastructure in the SSB sites as described in Appendix (G) for addresses of physical sites and refer to Appendix (I) |  |  | Included
55 | 1 | 6.1 | Telecommunication infrastructure in the SSB sites overall design and deployement plan
56 | 1 | 6.2 | Telecommunication infrastructure deployment in the SSB headquarters (1x 25 nodes, Wi-Fi modem and hot spot to 3G/4G)
57 | 1 | 6.3 | Telecommunication infrastructure deployment in the SSB township offices (77 nodes, Wi-Fi modem and hot spot to 3G/4G)
58 | 1 | 6.4 | Telecommunication infrastructure deployment in the SSB medical clinics (96 nodes, Wi-Fi modem and hot spot to 3G/4G)
59 | 1 | 6.5 | Telecommunication infrastructure deployment in the SSB hospitals (3 nodes, Wi-Fi modem and hot spot to 3G/4G)
60 | 1 | 6.6 | Telecommunication infrastructure deployment in the SSB State and region offices and SSB District offices (14+38 = 52 nodes, Wi-Fi modem and hot spot to 3G/4G)
61 | 1 | 6.7 | Testing
62
63 | 1 | 7.0 | Telecommunication bandwidth for all SSB sites |  |  | Included
64 | 1 | 7.1 | Telecommunication bandwidth monthly cost for all SSB sites (detailed invoice per site) as described in Appendix (J)
65
66 | 1 | 8.0 | Development and production Environment infrastructure |  |  | Included
67 | 1 | 8.1 | Development and production Environment infrastructure design and installation plan
68 | 1 | 8.2 | Development infrastructure installation,
69 | 1 | 8.3 | Production infrastructure installation
70 | 1 | 8.4 | System versioning mechanism and Migration tool(s)
71 | 1 | 8.5 | Versionning Migration procedure
72 | 1 | 8.6 | Development and production Environment infrastructure testing
73 | 1 | 8.7 | Development and production Environment infrastructure training for SSB IT (20 people)
74
75 | 2 | 9.0 | Imaging Process |  |  | Included
76 | 2 | 9.1 | Imaging process Design
77 | 2 | 9.2 | Imaging process code development (Any imaging solution or software package may be used)
78 | 2 | 9.3 | Testing
79 | 2 | 9.4 | Integration test
80 | 2 | 9.5 | Evolution and integrity control of the code for the duration of the project
81
82 | 2 | 10.0 | Imaging Hardware (Detail Scanner specification can see at Appendix (I)) |  |  | Included
83 | 2 | 10.1 | Automatic Feeding Scanner (250 for all SSB facilities)
84 | 2 | 10.2 | Overhead Scanner (250 for all SSB facilities)
85
86 | 1 | 11.0 | Microsoft license with assurance service ( tech support and maintenance) |  |  | Included |  | Not applicable
87 | 1 | 11.1 | .NET platform
88 | 1 | 11.2 | MS-SERVER 2016
89 | 1 | 11.3 | MS-SQL database and encryption
90 | 1 | 11.4 | FRAMEWORK
91 | 1 | 11.5 | Email Microsoft exchange for all SSB
92 | 1 | 11.6 | Detail inventory of all Microsoft software component
93 | 1 | 11.7 | Microsoft software installation and integration in the data center
94 |  |  | Part No. Item Name Qty
95 | 1 | 11.7.1 | 9GS-00112 CISSteDCCore LicSAPk OLP 2Lic NL Gov CoreLic Qlfd 50
96 | 1 | 11.7.2 | R18-05159 WinSvrCAL 2016 OLP NL Gov UsrCAL 2300
97 | 1 | 11.7.3 | 7JQ-01300 SQLSvrEntCore 2017 OLP 2Lic NL Gov CoreLic Qlfd 16
98 | 1 | 11.7.4 | 312-04365 ExchgSvrStd 2016 OLP NL Gov 4
99 | 1 | 11.7.5 | 381-04429 ExchgStdCAL 2016 OLP NL Gov DvcCAL 2300
100 | 1 | 11.7.6 | 77D-00105 VSProSubMSDN LicSAPk OLP NL Gov Qlfd 40
101 | 1 | 11.7.7 | MX3-00110 VSEntSubMSDN LicSAPk OLP NL Gov Qlfd 3
102 | 1 | 11.7.8 | 076-05692 Prjct 2016 OLP NL Gov 10
103 | 1 | 11.7.9 | R39-01199 WinSvrExtConn 2016 OLP NL Gov Qlfd 6
104 | 1 | 11.7.10 | N\A Azure B2C Basic User & Authentication per year - 1 million users 1
105 | 1 | 11.7.11 | FQC-09482 WinPro 10 MVL Legalization GetGenuine Large Organization 200
106
107 | 1 | 12.0 | Microsoft Office License |  |  | Included |  | Not applicable
108 | 1 | 12.1 | 021-10583 OfficeStd 2016 OLP NL Gov (Only Word, Excel and PowerPoint) 1000
109 | 1 | 12.2 | D86-05728 VisioStd 2016 OLP NL Gov 20
110
111 | 1 | 13.0 | EMAIL Service solution
112 | 1 | 13.1 | EMAIL solution service design (Policy, Rules, Operation Procedure)
113 | 1 | 13.2 | EMAIL solution service configration and deployment
114 |  | 13.3 | EMAIL solution service user training
115
116 | 1 | 14.0 | Server virtualization solution |  |  | Included
117 | 1 | 14.1 | Server virtualiztion solution (Microsoft or other) design and installation plan
118 | 1 | 14.2 | Server virtualiztion solution installation
119 | 1 | 14.3 | Server virtualiztion solution training
120
121 | 1 | 15.0 | Android software environment |  |  | Included |  | Not applicable
122 | 1 | 15.1 | Android studio environment design and installation plan
123 | 1 | 15.2 | Android Software development kit (SDK)
124 | 1 | 15.3 | Mobile Replication tools (Data synchronisation for off line use) for 300 users
125 | 1 | 15.4 | Mobiles application server implementation in the data center
126 | 1 | 15.5 | Android development tools environment integration and installation
127 | 1 | 15.6 | Final inventory of all Android software component
128
129 | 1 | 16.0 | Business Intelligence platform |  |  | Included |  | Not applicable
130 | 1 | 16.1 | Business Intelligence platform design and installation plan (using Power BI Report Server with private cloud using Azure B2C)
131 | 1 | 16.2 | Business Intelligence platform implementation in the datacenter
132 | 1 | 16.3 | Business Intelligence platform testing
133 | 1 | 16.4 | Business Intelligence platform SSB IT staff (10) and super user (20) training
134
135 | 1 | 17.0 | IT Staff basic training for Microsoft platform |  |  | Included | Not applicable | Not applicable
136 | 1 | 17.1 | Microsoft .NET environment
137 | 1 | 17.2 | Microsoft MS-SERVER
138 | 1 | 17.3 | Microsoft MS-SQL DB
139 | 1 | 17.4 | Microsoft Virtualization environment
140 | 1 | 17.5 | Programming language related to the SSB Microsoft environment
141
142 | 1 | 18.0 | IT Staff training for Android platform |  |  | Included | Not applicable | Not applicable
143 | 1 | 18.1 | Android environment
144 | 1 | 18.2 | Android Studio
145 | 1 | 18.3 | Android SDK
146 | 1 | 18.4 | Programming language related to the Android environment
147
148 | 1 | 19.0 | IT Staff training for BI platform |  |  | Included | Not applicable | Not applicable
149 | 1 | 19.1 | BI environment
150 | 1 | 19.2 | BI data base environment administration
151 | 1 | 19.3 | ETL programming
152 | 1 | 19.4 | BI reporting tools for IT resources
153 | 1 | 19.5 | BI Dashboard tools for IT resources
154 | 1 | 19.6 | BI reporting tools for super users
155 | 1 | 19.7 | BI Dashboard tools for super users
156
157 | 1 | 20.0 | Laptops, PCs, Printers and mobile devices - GROUP 1 |  |  | Included |  | Not applicable
158 | 1 | 20.1 | Provide and configure 40 Desktop PCs for IT Staff (programmer)
159 | 1 | 20.2 | Provide and configure 20 Desktop PCs for power users
160 | 1 | 20.3 | Provide and configure 700 Laptops with 3G/4G modems for end users
161 | 1 | 20.4 | Provide and configure 300 Electronic tablets for end users
162 | 1 | 20.5 | Provide and configure 400 Laser printers
163 | 1 | 20.6 | Deploy Laptop and Electronic devices according to project phases
164 | 1 | 20.7 | Deploy Laser printers according to project phases
165
166 | 1 | 21.0 | Laptops, PCs, Printers and mobile devices - GROUP 2 |  |  | Included |  | Not applicable
167 | 1 | 21.1 | Provide and configure 5 Desktop PCs for IT Staff (programmer)
168 | 1 | 21.2 | Provide and configure 5 Laptops with 3G/4G modems for power users
169 | 1 | 21.3 | Provide and configure 50 Laptops with 3G/4G modems for end users
170 | 1 | 21.4 | Provide and configure 30 Electronic tablets for end users
171 | 1 | 21.5 | Provide and configure 30 Laser printers
172 | 1 | 21.6 | Deploy Laptop and Electronic devices according to project phases
173 | 1 | 21.7 | Deploy Laser printers according to project phases
174
175 | 1 | 22.0 | Development environment training and support |  |  | Included |  | Not applicable
176 | 1 | 22.1 | Methodology and procedures for application development within the Microsoft environment - training for 60 people;
177 | 1 | 22.2 | Specific training and development environment support on the Microsoft platform
178 | 1 | 22.3 | Programming technique training for the Microsoft IT team (up to 40 people)
179 | 1 | 22.4 | Methodology and procedures for application development within the Android environment - training for 30 people
180 | 1 | 22.5 | Specific training and development environment support on the Android platform
181 | 1 | 22.6 | Programming technique training for the Android IT team (up to 20 people)
182 | 1 | 22.7 | Provide continuous support to IT team with respect to all development environments
183
184 | 1 | 23.0 | Access and security control process development |  |  | Included |  | Not applicable
185 | 1 | 23.1 | User identification and authentication mechanism Design
186 | 1 | 23.2 | Identification dialogue and common Web interface development
187 | 1 | 23.3 | Identification dialogue and common Mobile interface development
188 | 1 | 23.4 | Access and security control administration mechanism
189 | 1 | 23.5 | Integration test
190 | 1 | 23.6 | Acceptance test
191
192 | 1 | 24.0 | Common user Web interface development |  |  | Included |  | Not applicable
193 | 1 | 24.1 | Common user Web interface Design
194 | 1 | 24.2 | Common user Web interface development
195 | 1 | 24.3 | Integration test
196 | 1 | 24.4 | User test
197
198 | 1 | 25.0 | Common user Mobile interface development |  |  | Included |  | Not applicable
199 | 1 | 25.1 | Common user Mobile interface Design
200 | 1 | 25.2 | Common user Mobile interface development
201 | 1 | 25.3 | Integration test
202 | 1 | 25.4 | User test
203
204 | 1 | 25.0 | Event processor development |  |  | Included |  | Not applicable
205 | 1 | 25.1 | Event processor Design
206 | 1 | 25.2 | Event processor code development
207 | 1 | 25.3 | Testing
208 | 1 | 25.4 | Integration test
209 | 1 | 25.5 | Evolution and integrity control of the code for the duration of the project
210
211 | 1 | 26.0 | Data Migration from Old Database(Already Cleaned by SSB) to New Database |  |  | Included |  | Not applicable
212 | 1 | 26.1 | Data Migration Process design
213 | 1 | 26.2 | Data Migration code development
214 | 1 | 26.3 | Testing and trial
215 | 1 | 26.4 | Acceptance test in the integration test development environment
216 | 1 | 26.5 | Database automated migration
217 | 1 | 26.6 | New database verification and problem remediation
218
219 | 1 | 27.0 | Data entry service (registration and contribution) |  |  | Included |  | Not applicable
220 | 1 | 27.1 | Data entry function design
221 | 1 | 27.2 | Data entry function development
222 | 1 | 27.3 | Data entry function deployment
223 | 1 | 27.4 | Manual data entry service for 1 500 000 pages
224
225 | 1 | 28.0 | Employer registration process development (Form # 1) - Web development |  |  | Included |  | Not applicable
226 | 1 | 28.1 | Process design
227 | 1 | 28.2 | Application code development
228 | 1 | 28.3 | Testing
229 | 1 | 28.4 | Acceptance test in the development environment
230 | 1 | 28.5 | Trial period in 1 Township, at Headquarters and some employers
231
232 | 1 | 29.0 | Employer registration process development (Form # 1) - Mobile development |  |  | Included |  | Not applicable
233 | 1 | 29.1 | Process design
234 | 1 | 29.2 | Application code development
235 | 1 | 29.3 | Testing
236 | 1 | 29.4 | Acceptance test in the development environment
237 | 1 | 29.5 | Trial period in 1 Township, at Headquarters and some employers
238 | 1 | 29.6 | Deployment according the planning
239
240 | 1 | 30.0 | Worker registration process web development (Form # 2) - Web development |  |  | Included |  | Not applicable
241 | 1 | 30.1 | Process design
242 | 1 | 30.2 | Picture and biometric capture integrated application design
243 | 1 | 30.3 | Application code development including picture and biometric integration
244 | 1 | 30.4 | Testing
245 | 1 | 30.5 | Acceptance test in the development environment
246
247 | 1 | 31.0 | Worker registration process web development (Form # 2) - Mobile development |  |  | Included |  | Not applicable
248 | 1 | 31.1 | Process design
249 | 1 | 31.2 | Picture and biometric capture integrated application design
250 | 1 | 31.3 | Application code development including picture and biometric integration
251 | 1 | 31.4 | Testing
252 | 1 | 31.5 | Acceptance test in the development environment
253
254 | 1 | 32.0 | Employer contribution process (Phase 1) - web development (Form # 13 ) - Web development |  |  | Included |  | Not applicable
255 | 1 | 32.1 | Process design with EMoney
256 | 1 | 32.2 | Application code development
257 | 1 | 32.3 | EMoney solution realization
258 | 1 | 32.4 | Testing
259 | 1 | 32.5 | Acceptance test in the development environment
260
261 | 1 | 33.0 | Claim process - work related temporary injury and sickness (Phase 1) - Web development |  |  | Included |  | Not applicable
262 | 1 | 33.1 | Process design
263 | 1 | 33.2 | Application code development
264 | 1 | 33.3 | Testing
265 | 1 | 33.4 | Acceptance test in development environment
266
267 | 1 | 34.0 | Benefit payment process for- work related temporary injury and sickness (Phase 1) With cash - Web development |  |  | Included |  | Not applicable
268 | 1 | 34.1 | Process design
269 | 1 | 34.2 | Application code development
270 | 1 | 34.3 | Testing
271 | 1 | 34.4 | Acceptance test in the development environment
272
273
274 | 1 | 35.0 | Benefit payment process for- work related temporary injury and sickness (Phase 1) With electronic money- Web development |  |  | Included |  | Not applicable
275 | 1 | 35.1 | Process design
276 | 1 | 35.2 | Application code development
277 | 1 | 35.3 | Testing
278 | 1 | 35.4 | Acceptance test in the development environment
279
280 | 1 | 36.0 | Electronic money management |  |  | Included |  | Not applicable
281 | 1 | 36.1 | Process (contribution and benefits payment) design
282 | 1 | 36.2 | Application code development
283 | 1 | 36.3 | Testing
284 | 1 | 36.4 | Acceptance test in the development environment
285
286 | 1 | 37.0 | Smart ID Card printing Central environment in NayPyitaw |  |  | Included
287 | 1 | 37.1 | SMART ID Card with finger print and IRIS capable Solution Design (Detail SMART card specification can see at Appendix (I))
288 | 1 | 37.2 | Card printer and servers infrastructure (Redundant inorder to support continuous operation at peak time)
289 | 1 | 37.3 | Card printer and servers solution deployment
290 | 1 | 37.4 | Testing
291 | 1 | 37.5 | Card printer operation training
292 | 1 | 37.6 | Card printer maintenance and operation training
293
294 | 1 | 38.0 | SMART ID Card printing supplies (for the project)
295 | 1 | 38.1 | SMART ID Card printing supplies for 1 500 000 cards for the first 3 years of project operations |  |  | Not applicable | Not applicable | Not applicable
296
297 | 1 | 40.0 | Additional SMART ID Card printing supplies
298 | 1 | 40.1 | SMART ID Card printing supplies additional 500 000 cards |  |  | Not applicable | Not applicable | Not applicable
299 | 1 | 40.2 | SMART ID Card printing supplies additional 500 000 cards |  |  | Not applicable | Not applicable | Not applicable
300 | 1 | 40.3 | SMART ID Card printing supplies additional 500 000 cards |  |  | Not applicable | Not applicable | Not applicable
301 | 1 | 40.4 | SMART ID Card printing supplies additional 500 000 cards |  |  | Not applicable | Not applicable | Not applicable
302 | 1 | 40.5 | SMART ID Card printing supplies additional 500 000 cards |  |  | Not applicable | Not applicable | Not applicable
303 | 1 | 40.6 | SMART ID Card printing supplies additional 500 000 cards |  |  | Not applicable | Not applicable | Not applicable
304
305 | 1 | 41.0 | Card reader, Fingerprint scanner and picture solution for single and/or ten fingerprints(Detail specification can see at Appendix (I)) ***Only one out of the two option can be selected by SSB***
306 | 1 | 41.1.0 | Single Fingerprint Solution |  |  | Included |  | Not applicable
306 | 1 | 41.1.1 | Specific operating Card reader, fingerprint reader and picture Solution Design- Single Fingerprint Solution
307 | 1 | 41.1.2 | Camera, Card reader, Single Fingerprint scanner and Fingerprint reader x 721 deployment
308 | 1 | 41.1.3 | Camera, Card reader,Single Fingerprint scanner and Fingerprint reader x 100 deployment (Mobile Station Kit)
309 | 1 | 41.1.4 | Card reader,Single Fingerprint reader and scanner maintenance and operating training
310
311 | 1 | 41.2.0 | Ten Fingerprint Solution |  |  | Included |  | Not applicable
312 | 1 | 41.2.1 | Specific operating Card reader, fingerprint reader and picture Solution Design- Ten Fingerprint Solution
313 | 1 | 41.2.2 | Camera, Card reader,Ten Fingerprint scanner and Fingerprint reader x 721 deployment
314 | 1 | 41.2.3 | Camera, Card reader, Ten Fingerprint scanner and Fingerprint reader x 100 deployment (Mobile Station Kit)
315 | 1 | 41.2.4 | Card reader, Fingerprint reader and scanner maintenance and operating training
316
317
318 | 1 | 42.0 | IRIS scanning and processing capacity (optional) |  |  | Included |  | Not applicable
319 | 1 | 42.1 | IRIS scan solution design
320 | 1 | 42.2 | IRIS scanner for registration Process - Integration
321 | 1 | 42.3 | IRIS reader x 721 deployment
322 | 1 | 42.4 | IRIS reader x 100 deployment (Mobile Station Kit)
323 | 1 | 42.5 | Integrated Card reader, finger print reader and IRIS reader operation training
324 | 1 | 42.6 | Final approval
325
326 | 1 | 43.0 | Help desk solution, IP phone and operation service (optional) |  |  | Included |  | Not applicable
327 | 1 | 43.1 | Help desk operation solution design and IP phone platform
328 | 1 | 43.2 | Help desk Software solution deployment in the data center
329 | 1 | 43.3 | Help desk Software solution setting and IP phone integration
330 | 1 | 43.4 | IP phone system software installation in the data center.
331 | 1 | 43.5 | IP phone (30 devices) deployment in the SSB headquarters
332 | 1 | 43.6 | 20 dedicated phone lines (phone numbers dedicated to the help desk)
333 | 1 | 43.7 | Test
334 | 1 | 43.8 | Help desk detail procedure (who is responsible for what)
335 | 1 | 43.9 | Help desk solution and organization implementation
336 | 1 | 43.10 | Training on the helpdesk and the IP phone to 40 resources
337 | 1 | 43.11 | Trial
338 | 1 | 43.12 | Deployment and Final approval
339
340 | 1 | 44.0 | Informational public Website with Myanmar and English (optional) |  |  | Included |  | Not applicable
341 | 1 | 44.1 | Informational Website solution design (with hosting in the data center)
342 | 1 | 44.2 | Informational Website realization
343 | 1 | 44.3 | Informational Website solution SSB communication staff training
344 | 1 | 44.4 | Informational Website solution deployment
345
346 | 1 | 45.0 | Training strategy and planning for Phase 1 |  |  | Not applicable | Not applicable | Not applicable
347 | 1 | 45.1 | Training strategy (which users should receive which training and in what sequence)
348 | 1 | 45.2 | Training plan (what, when, for whom, logistics)
349
350 | 1 | 46.0 | General system training for SSB users for Phase 1 |  |  | Not applicable | Not applicable | Not applicable
351 | 1 | 46.1 | Preparation of training material
352 | 1 | 46.2 | Training session according to plan
353
354 | 1 | 47.0 | Train the trainer for Employer process for Phase 1 |  |  | Not applicable | Not applicable | Not applicable
355 | 1 | 47.1 | Preparation of training material
356 | 1 | 47.2 | Training session according to plan
357
358 | 1 | 48.0 | SSB user training for phase 1 business processes |  |  | Not applicable | Not applicable | Not applicable
359 | 1 | 48.1 | Preparation of training material
360 | 1 | 48.2 | Training session according to plan
361
362 | 1 | 49.0 | Pilot test for phase 1 (at least two townships and two clinics in Yangon Region) |  |  | Not applicable | Not applicable | Not applicable
363 | 1 | 49.1 | Detail deployment plan for pilot (logistics, synchronisation with training and equipment deployment)
364 | 1 | 49.2 | Trial stage
365 | 1 | 49.3 | Complete deployment across two townships and two clinics in Yangon Region
366 | 1 | 49.4 | Deployment monitoring
367 | 1 | 49.5 | Lesson Learn document
368
369 | 1 | 50.0 | Application deployment for phase 1 (for all SSB Sites) |  |  | Not applicable | Not applicable | Not applicable
370 | 1 | 50.1 | Detail deployment plan (logistics, synchronisation with training and equipment deployment)
371 | 1 | 50.2 | Trial stage
372 | 1 | 50.3 | Complete deployment across all SSB sites
373 | 1 | 50.4 | Deployment monitoring
374 | 1 | 50.5 | Deployment approval
375
376 | 2 | 51.0 | Solution design for Phase 2 |  |  | Included | Not applicable | Not applicable
377 | 2 | 51.1 | Phase 2 system design (overview)
378 | 2 | 51.2 | Completion of Data model (entity relation model)
379 | 2 | 51.3 | Completion of all Core Business process model high level
380 | 2 | 51.4 | Testing strategy for phase2 - strategy and plan
381
382 | 2 | 52.0 | BI ETL and storage solution for core business process - Realization |  |  | Included |  | Not applicable
383 | 2 | 52.1 | BI, ETL and storage design
384 | 2 | 52.2 | BI and storage environment configuration and parameterization
385 | 2 | 52.3 | ETL development for core business process
386 | 2 | 52.4 | Preliminary loading of all available data (mainly from registration)
387 | 2 | 52.5 | Testing
388 | 2 | 52.6 | Acceptance test in the development environment
389
390 | 2 | 53.0 | Reports development using BI environment - Realization |  |  | Included |  | Not applicable
391 | 2 | 53.1 | Report building process design
392 | 2 | 53.2 | Reports framework and standard report development
393 | 2 | 53.3 | Reports development for all business process
394 | 2 | 53.4 | Testing
395 | 2 | 53.5 | Acceptance test in the development environment
396
397 | 2 | 54.0 | Dashboard development using BI environment - Realization |  |  | Included |  | Not applicable
398 | 2 | 54.1 | Dashboard building process design
399 | 2 | 54.2 | Dashboard framework setting or development
400 | 2 | 54.3 | Dashboard development for all department directors' processes
401 | 2 | 54.4 | Testing
402 | 2 | 54.5 | Acceptance test in the development environment
403
404 | 2 | 55.0 | Insurance standard program processor for Health and Social care, Family Assistance, Employment injury Benefits, Unemployment.- Development |  |  | Included |  | Not applicable
405 | 2 | 55.1 | Process design
406 | 2 | 55.2 | Application code development
407 | 2 | 55.3 | Testing
408 | 2 | 55.4 | Acceptance test in the development environment
409
410 | 2 | 56.0 | Benefit categories processor - Development |  |  | Included |  | Not applicable
411 | 2 | 56.1 | Process design
412 | 2 | 56.2 | Application code development
413 | 2 | 56.3 | Testing
414 | 2 | 56.4 | Acceptance test in the development environment
415
416 | 2 | 57.0 | Medical services provision process ( HEALTH RECORD updates AND else) - Web development |  |  | Included |  | Not applicable
417 | 2 | 57.1 | Medical clinic Process design
418 | 2 | 57.2 | Application code development
419 | 2 | 57.3 | Testing
420 | 2 | 57.4 | Acceptance test in the development environment
421
422 | 2 | 58.0 | Medical services provision process ( HEALTH RECORD updates AND else) - Mobile development |  |  | Included |  | Not applicable
423 | 2 | 58.1 | Medical clinic Process design
424 | 2 | 58.2 | Application code development
425 | 2 | 58.3 | Testing
426 | 2 | 58.4 | Acceptance test in the development environment
427
428 | 2 | 59.0 | Medicine/supply management process - Web development |  |  | Included |  | Not applicable
429 | 2 | 59.1 | Process design
430 | 2 | 59.2 | Code development
431 | 2 | 59.3 | Testing
432 | 2 | 59.4 | Acceptance test in the development environment
433
434 | 2 | 60.0 | Claim process - work related temporary injury and sickness process - Web development |  |  | Included |  | Not applicable
435 | 2 | 60.1 | Process design
436 | 2 | 60.2 | Application code development
437 | 2 | 60.3 | Testing
438 | 2 | 60.4 | Acceptance test in the development environment
439
440 | 2 | 61.0 | Claim process - work related permanent injury and sickness process - Web development |  |  | Included |  | Not applicable
441 | 2 | 61.1 | Process design
442 | 2 | 61.2 | Application code development
443 | 2 | 61.3 | Testing
444 | 2 | 61.4 | Acceptance test in the development environment
445
446 | 2 | 62.0 | Claim process -survivor benefits for occupational decease process - Web development |  |  | Included |  | Not applicable
447 | 2 | 62.1 | Process design
448 | 2 | 62.2 | Application code development
449 | 2 | 62.3 | Testing
450 | 2 | 62.4 | Acceptance test in the development environment
451
452 | 2 | 63.0 | Claim for Maternity leave process - Web development |  |  | Included |  | Not applicable
453 | 2 | 63.1 | Process design
454 | 2 | 63.2 | Application code development
455 | 2 | 63.3 | Testing
456 | 2 | 63.4 | Acceptance test in the development environment
457
458 | 2 | 64.0 | Claim for funeral expense process - Web development |  |  | Included |  | Not applicable
459 | 2 | 64.1 | Process design
460 | 2 | 64.2 | Application code development
461 | 2 | 64.3 | Testing
462 | 2 | 64.4 | Acceptance test in the development environment
463
464 | 2 | 65.0 | Claim for children Scholastic stipend process - Web development |  |  | Included |  | Not applicable
465 | 2 | 65.1 | Process design
466 | 2 | 65.2 | Application code development
467 | 2 | 65.3 | Testing
468 | 2 | 65.4 | Acceptance test in the development environment
469
470 | 2 | 66.0 | Claim for assistance for natural disaster process - Web development |  |  | Included |  | Not applicable
471 | 2 | 66.1 | Process design
472 | 2 | 66.2 | Application code development
473 | 2 | 66.3 | Testing
474 | 2 | 66.4 | Acceptance test in the development environment
475
476 | 2 | 67.0 | Worker voluntary contribution process - Web development |  |  | Included |  | Not applicable
477 | 2 | 67.1 | Process design
478 | 2 | 67.2 | Application code development
479 | 2 | 67.3 | Testing
480 | 2 | 67.4 | Acceptance test in the development environment
481
482 | 2 | 68.0 | Pension registration process - Web development |  |  | Included |  | Not applicable
483 | 2 | 68.1 | Process design
484 | 2 | 68.2 | Application code development
485 | 2 | 68.3 | Testing
486 | 2 | 68.4 | Acceptance test in the development environment
487
488 | 2 | 69.0 | Employer inspection process (by the Township) - Web development |  |  | Included |  | Not applicable
489 | 2 | 69.1 | Process design
490 | 2 | 69.2 | Application code development
491 | 2 | 69.3 | Testing
492 | 2 | 69.4 | Acceptance test in the development environment
493
494 | 2 | 70.0 | Labour inspection process (FGLLID) - Web development |  |  | Included |  | Not applicable
495 | 2 | 70.1 | Process design
496 | 2 | 70.2 | Application code development
497 | 2 | 70.3 | Testing
498 | 2 | 70.4 | Acceptance test in the development environment
499
500 | 2 | 71.0 | FDA File (soft file) update and import process - Web development |  |  | Included |  | Not applicable
501 | 2 | 71.1 | Process design (list updating dialog and electronic file transfer)
502 | 2 | 71.2 | Application code development
503 | 2 | 71.3 | Testing
504 | 2 | 71.4 | Acceptance test in the development environment
505
506 | 2 | 72.0 | Electronic money management Phase 2 |  |  | Included |  | Not applicable
507 | 2 | 72.1 | Process (contribution and benefits payment) design for phase 2
508 | 2 | 72.2 | Application code development
509 | 2 | 72.3 | Testing
510 | 2 | 72.4 | Acceptance test in the development environment
511
512 | 2 | 73.0 | Application deployment for phase 2 (for all SSB Sites) |  |  | Not applicable | Not applicable | Not applicable
513 | 2 | 73.1 | Detail deployment plan (logistics, synchronisation with training and equipment deployment)
514 | 2 | 73.2 | Trial stage
515 | 2 | 73.3 | Complete deployment across all SSB sites
516 | 2 | 73.4 | Deployment monitoring
517 | 2 | 73.5 | Deployment approval
518
519 | 3 | 74.0 | Phase 3 solution design overview |  |  | Included | Not applicable | Not applicable
520 | 3 | 74.1 | solution design overview
521
522 | 3 | 75.0 | System administration process |  |  | Included |  | Not applicable
523 | 3 | 75.1 | Process design (this is about managing all the parameters in the system such as: automatic reports, updating the SSB calendar, adding or modifying new SSB sites and medical clinics)
524 | 3 | 75.2 | Application code development
525 | 3 | 75.3 | End user procedure documentation
526 | 3 | 75.4 | Testing
527 | 3 | 75.5 | Acceptance test in the development environment
528
529 | 3 | 76.0 | SSB Accounting process (Annual report, Balance sheet, Grand Ledger, Funds) |  |  | Included |  | Not applicable
530 | 3 | 76.1 | Process design
531 | 3 | 76.2 | Software installation in the data center
532 | 3 | 76.3 | Software setting (and code development if required)
533 | 3 | 76.4 | Testing
534 | 3 | 76.5 | Trial period
535 | 3 | 76.6 | Acceptance test in the development environment
536 | 3 | 76.7 | Training
537
538 | 3 | 77.0 | SSB human resources management process |  |  | Included |  | Not applicable
539 | 3 | 77.1 | Process design
540 | 3 | 77.2 | Software installation in the data center
541 | 3 | 77.3 | Software setting (and code development if required)
542 | 3 | 77.4 | Testing
543 | 3 | 77.5 | Trial period
544 | 3 | 77.6 | Acceptance test in the development environment
545 | 3 | 77.7 | Training
546
547 | 3 | 78.0 | SSB building and inventory maintenance management process |  |  | Included |  | Not applicable
548 | 3 | 78.1 | Process design
549 | 3 | 78.2 | Software installation in the data center
550 | 3 | 78.3 | Software setting (and code development if required)
551 | 3 | 78.4 | Testing
552 | 3 | 78.5 | Trial period
553 | 3 | 78.6 | Acceptance test in the development environment
554 | 3 | 78.7 | Training
555
556 | 3 | 79.0 | Hospital management process for Centralized Admission, Dismiss and Transfer (ADT) |  |  | Included |  | Not applicable
557 | 3 | 79.1 | Hospital Process design
558 | 3 | 79.2 | Hospital Software implementation and configuration setting in the Data center
559 | 3 | 79.3 | Hospital Software deployment
560 | 3 | 79.4 | Testing
561 | 3 | 79.5 | Acceptance test in the development environment
562 | 3 | 79.6 | Trial period in one hospital
563 | 3 | 79.7 | Hospital Software rollout in all hospitals
564 | 3 | 79.8 | Training
565
566 | 3 | 80.0 | MOBILE version of the business process (Deliverable No. 32 to 35; 59 to 70) |  |  | Included |  | Not applicable
567 | 3 | 80.1 | Process design
568 | 3 | 80.2 | Application code development
569 | 3 | 80.3 | Testing
570 | 3 | 80.4 | Acceptance test in the development environment
571 | 3 | 80.5 | Trial period in 1 Township, at the Headquarters and at some employers
572 | 3 | 80.6 | Deployment according the planning
573
574 | 3 | 81.0 | Undefined deliverable Number 1 (price = 0.01 % of total cost including maintenance during the 3 years duration of the project) |  |  | Included |  | Not applicable
575 | 3 | 81.1 | Design
576 | 3 | 81.2 | Realization
577 | 3 | 81.3 | Acceptation test in development environment
578
579 | 3 | 82.0 | Undefined deliverable Number 2 (price = 0.01 % of total cost including maintenance during the 3 years duration of the project) |  |  | Included |  | Not applicable
580 | 3 | 82.1 | Design
581 | 3 | 82.2 | Realization
582 | 3 | 82.3 | Acceptation test in development environment
583
584 | 3 | 83.0 | Undefined deliverable Number 3 (price = 0.01 % of total cost including maintenance during the 3 years duration of the project) |  |  | Included |  | Not applicable
585 | 3 | 83.1 | Design
586 | 3 | 83.2 | Realization
587 | 3 | 83.3 | Acceptance test in the development environment
588
589 | 3 | 84.0 | Solution final delivery approval |  |  | Included | Included | Included
590 | 3 | 84.1 | Final approval and official start of maintenance period | included | included
591
592
593 | Maint. |  | MAINTENANCE PHASE
594
595 | Maint. | 85.0 | Data center maintenance and operation |  |  | Included |  | Not applicable
596 | Maint. | 85.1 | Standard level agreement for 24 hour/7 day operation, up time required is 8 hours per business day
597 | Maint. | 85.2 | Maintenance procedure manual
598 | Maint. | 85.3 | Annual Maintenance plan (foreseeable upgrades for all software components related to the data center)
599 | Maint. | 85.4 | Operation service (monitoring, backup and recovery, preventive actions …)
600 | Maint. | 85.5 | Maintenance service (regular software upgrade, hardware repairs or replacement, on line assistance from hardware and software makers for problem solving)
601
602 | Maint. | 86.0 | Card printing maintenance and operation |  |  | Included |  | Not applicable
603 | Maint. | 86.1 | Standard level agreement for 24hour/7day operation, up time required is 48 hours
604 | Maint. | 86.2 | Maintenance procedure manual
605 | Maint. | 86.3 | Annual Maintenance plan (foreseeable up grade for all software components, and short life parts replacement)
606 | Maint. | 86.4 | Operation service (production operation, monitoring, supply servicing, quality control of card production …)
607 | Maint. | 86.5 | Maintenance service (regular software up grade, hardware repairs or replacement, on line assistance from hardware and software makers for problem solving)
608
609 | Maint. | 87.0 | All PC, Laptop and Electronic tablets maintenance (including OS and anti virus protection) |  |  | Included |  | Not applicable
610 | Maint. | 87.1 | Standard level agreement for 8 h/5 business days operation (Onsite services using Help Desk see Deliverable No 43)
611 | Maint. | 87.2 | Maintenance procedure manual
612 | Maint. | 87.3 | Maintenance service (software upgradee If required, hardware repairs or replacement, on line assistance from hardware and software makers for problem solving)
613
614 | Maint. | 88.0 | Microsoft software annual licensing and maintenance |  |  | Included |  | Not applicable
615 | Maint. | 88.1 | Standard level agreement for 24h /7 days operation
616 | Maint. | 88.2 | Maintenance procedure manual
617 | Maint. | 88.3 | Annual Maintenance plan (foreseeable up grade for all software components)
618 | Maint. | 88.4 | Annual licensing coverage for all Microsoft software (excluding PC laptop and tablets)
619 | Maint. | 88.5 | Maintenance service (required software up grade, on line assistance from hardware and software makers for problem solving)
620
621 | Maint. | 89.0 | Business Intelligence platform annual licensing and maintenance |  |  | Included |  | Not applicable
622 | Maint. | 89.1 | Standard level agreement for 24h /7 days operation
623 | Maint. | 89.2 | Maintenance procedure manual
624 | Maint. | 89.3 | Annual Maintenance plan (foreseeable up grade for all software components)
625 | Maint. | 89.4 | Annual licensing coverage for all Business intelligence platform (including power users PC)
626 | Maint. | 89.5 | Maintenance service (required software up grade, on line assistance from hardware and software makers for problem solving)
627
628 | Maint. | 90.0 | All Software Packages annual licensing and maintenance |  |  | Included |  | Not applicable
629 | Maint. | 90.1 | Standard level agreement for 24h /7 days operation
630 | Maint. | 90.2 | Maintenance procedure manual
631 | Maint. | 90.3 | Annual Maintenance plan (foreseeable up grade for all software components)
632 | Maint. | 90.4 | Annual licensing coverage for all Software Package (including power users PC)
633 | Maint. | 90.5 | Maintenance service (required software up grade, on line assistance from hardware and software makers for problem solving) |  |  | Included |  | Not applicable
|  |  | TOTAL | 0 | 0 | Included | 0 | 0
|  |  | GRAND TOTAL (including Mandatory deliverables and optional deliverables and annual maintenance cost and annual operational cost) | 0
Full name and surname of authorized supplier representative:
Authorized supplier representative signature :
Date: